## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Research Structure of Sign Language | 2 | 1
2 | Research tokenizing sign language | 3 | 1
3 | Research how to take input | 2 | 1
4 | Identify programming language for ML | 2 | 1
5 | Determine what tech stack to use | 5 | 2
6 | Find training data | 5 | 2
7 | Reach out to sign language department | 5 | 1
8 | Mapping signs to letters | 3 | 2
9 | Translate signs into more human readable english | 13 | 5
10 | Map sign videos to english translations | 3 | 3
11 | Design UI | 5 | 3
12 | Create ML model for translations | 13 | 4
13 | Text to Speech | 3 | 6
14 | Identify letters | 8 | 3
15 | Identify numbers | 8 | 3
16 | Identity common english words | 13 | 4
17 | Text to sign lookup | 3 | 6
18 | Train ML model to recognize signs | 13 | 5
19 | Work on steps to increase the accuracy of model | 21 | 5
20 | Research ideal layers in ML model | 21 | 3
21 | Learn rudimentary sign language | 13 | 4
22 | Implement User interface | 5 | 4