## Sheet1
Team 23 - EECS 581
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Accounts Setup / GitHub Repos Created | 1 | 1
2 | Decide Hardware | 1 | 1
3 | Order Necessary Parts | 1 | 1
4 | Initial Hardware Setup | 3 | 1
5 | System can get power | 8 | 1
6 | write code to detect buttons being pressed | 13 | 2
7 | Prototype box, finalize circuit design | 3 | 3
8 | Program audio | 5 | 3
9 | Write code to allow synth waves to be changed | 13 | 3
10 | Be able to load sounds into board | 8 | 4
11 | Synth Engine | 13 | 5
12 | write basic framework of application (React) | 8 | 8
13 | write file transfer code for USB between computer and hardware | 5 | 8
14 | Desktop app is downloadable | 3 | 15
15 | Design and create final Box | 2 | 15
16 | Poster Detailing Project Produced | 3 | 20